## Summary tracker
Weekly/Daily Summary
| Nischal | Suraj | Overall
Total Samples This Week | 15 | 0 | 15
Average Daily Pace | 3.2 | #DIV/0! | #DIV/0!
Comment
Dataset Name | Start Date | Status | End Date for BE | QC Overview | Date of Artemis upload | Counts QC overview | End Date Artemis run | Done by | Summary slides | Comments
SRP225011 | 2026-04-27 | Artemis completed | 2026-04-30 | Samples look good |  | Nothing to note |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_420#slide=id.g3e98e108bb7_2_420 | The study had to be subsampled because some chirp-seq data was present
SRP017329 | NA |  | NA | NA | NA | NA | NA | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_460#slide=id.g3e98e108bb7_2_460 | SOLiD data
SRP323876 | 2026-05-04 | Artemis completed | 2026-05-04 | Nothing to note |  | Nothing to note |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_475#slide=id.g3e98e108bb7_2_475
SRP354339 | 2026-05-04 | Artemis completed | 2026-05-04 | Nothing to note |  | Nothing to note |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_525#slide=id.g3e98e108bb7_2_525
SRP548420 | 2026-05-05 | Artemis completed | 2026-05-12 | Nothing to note, some samples are single ended |  | More variance in a single cell type |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_928#slide=id.g3e98e108bb7_2_928
Break by client to check the already processed samples
SRP071203 | 2026-05-11 | Artemis completed | 2026-05-11 | Nothing to note |  | Nothing to note |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_624#slide=id.g3e98e108bb7_2_624 | No covariate information, unable to find DGEs in the paper, need to decide if this needs to be removed!
SRP329466 | 2026-05-11 | Artemis completed | 2026-05-12 | Removed 5 samples because of significant less number of reads mapped |  | Nothing to note |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e9fa34dab1_0_148#slide=id.g3e9fa34dab1_0_148 | No disease vs control as there is knockdown vs control
Break by client as they fix BE pipeline
SRP022028 | 2026-05-19 | Artemis completed | 2026-05-21 | The mapping percentage and other values look fine, but one sample has higher reads mapped | 2026-05-29 | Removed two samples as it was library size outlier, sample suffix 32 and 27 | 2026-06-01 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e560d87195_0_0#slide=id.g3e560d87195_0_0
SRP033725-hiseq | 2026-05-19 | Artemis completed | 2026-05-21 | Nothing to note | 2026-05-29 | Nothing to note | 2026-06-01 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e560d87195_0_39#slide=id.g3e560d87195_0_39 | instrument is hiseq 1000
SRP033725-ga | 2026-05-19 | Artemis completed | 2026-05-21 | Nothing to note | 2026-05-29 | Nothing to note | 2026-06-01 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e560d87195_0_39#slide=id.g3e560d87195_0_39 | instrument is genome analyser 2
SRP043684 | 2026-05-25 | Artemis completed | 2026-05-29 | Nothing to note | 2026-06-01 | Nothing to note | 2026-06-01 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_18#slide=id.g3e577a9a10f_0_18
SRP050376 | 2026-05-20 | Artemis completed | 2026-05-29 | Nothing to note | 2026-06-01 | Nothing to note | 2026-06-01 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_52#slide=id.g3e577a9a10f_0_52
SRP050377 | 2026-05-20 | Artemis completed | 2026-05-29 | Nothing to note | 2026-06-01 | Nothing to note | 2026-06-01 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_165#slide=id.g3e577a9a10f_0_165
Break by client as they fix BE pipeline
SRP073382 | 2026-05-29 | Artemis completed | 2026-06-01 | Need to remove sample 504 | 2026-06-02 | removing 521,522 : library size outlier | 2026-06-02 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_401#slide=id.g3e577a9a10f_0_401
SRP035524 | 2026-05-29 | Artemis completed | 2026-06-01 | Nothing to note for rna-seq samples | 2026-06-03 | Nothing to note | 2026-06-04 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3ecc791dd67_0_4#slide=id.g3ecc791dd67_0_4 | had a mix of rna-seq, midp-seq and chip-seq
SRP089857 | 2026-06-01 | Artemis completed | 2026-06-01 | Nothing to note | 2026-06-02 | Nothing to note | 2026-06-02 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_504#slide=id.g3e577a9a10f_0_504
SRP124299 | 2026-06-01 | Uploaded to Artemis | 2026-06-01 | Nothing to note | 2026-06-02 | waiting for response of timo |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_715#slide=id.g3e577a9a10f_0_715
SRP126056 | 2026-06-01 | Uploaded to Artemis | 2026-06-01 |  | 2026-06-02 |  |  | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_767#slide=id.g3e577a9a10f_0_767
SRP159190 | 2026-06-01 | Artemis completed | 2026-06-01 | Nothing to note | 2026-06-02 | Nothing to note | 2026-06-02 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_943#slide=id.g3e577a9a10f_0_943
SRP165962 | 2026-06-01 | Artemis completed | 2026-06-01 | Nothing to note | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3ecc791dd67_0_4#slide=id.g3ecc791dd67_0_4 | Nothing to note | 2026-06-02 | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_1066#slide=id.g3e577a9a10f_0_1066
SRP061192 | Cannot process these due to one of the following reasons 1. diseased and/or control samples are not present for the DGE(this is mostly because the study looks at knockdown of a specific gene or there are not enough replicates for a condition), 2. Covariates are mentioned in study but not provided in the metadata, please theck the slide link for more description | [6 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_217#slide=id.g3e577a9a10f_0_217
SRP061682 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_269#slide=id.g3e577a9a10f_0_269
SRP073163 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_322#slide=id.g3e577a9a10f_0_322
SRP090259 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_558#slide=id.g3e577a9a10f_0_558
SRP117268 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_665#slide=id.g3e577a9a10f_0_665
SRP135926 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_829#slide=id.g3e577a9a10f_0_829
SRP159245 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_1009#slide=id.g3e577a9a10f_0_1009
SRP188549 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_1278#slide=id.g3e577a9a10f_0_1278
SRP201367 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_1332#slide=id.g3e577a9a10f_0_1332
SRP212694 | [7 empty] | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e577a9a10f_0_1438#slide=id.g3e577a9a10f_0_1438
SRP156776 | 2026-06-02 | Artemis completed | 2026-06-02 | Nothing to note | 2026-06-03 | Nothing to note(for non-normalised counts there is weird clustering) | 2026-06-04 | Nischal
SRP182776 | 2026-06-02 | BE error | [5 empty] | Nischal
SRP183146 | 2026-06-02 | Artemis completed | 2026-06-02 | Nothing to note | 2026-06-03 | Nothing to note | 2026-06-04 | Nischal
SRP188467 | 2026-06-02 | BE error | [5 empty] | Nischal
SRP212636 | 2026-06-02 | BE error | [5 empty] | Nischal
SRP215268 | 2026-06-02 | Artemis completed | 2026-06-02 | Nothing to note | 2026-06-03 | There are a lot of DGEs | 2026-06-04 | Nischal
SRP223448 | 2026-06-02 | BE error | [5 empty] | Nischal
SRP074904 | 2026-06-02 | Artemis completed | 2026-06-02 | removed 8 samples as they didn't pass qc checks | 2026-06-03 | Samples are far in PCA probably due to unaccounted covariates | 2026-06-04 | Nischal | No info on covariates even though they have written in the paper about the covariates which are used

## Issue_tracker
StudyId | pubmedId | GSE_id | Issues | Severity | Comments
SRP061192 | 26824476 | GSE63734 | Sample source | Mild | skin biopsies -> fibroblast -> iPSC cell line
SRP061192 | 26824476 | GSE63734 | Assay type | Severe | all cases are CYFIP1 knockdowns
SRP061192 | 26824476 | GSE63734 | Cohort grouping | Severe | <3 replicates per group
SRP061682 | 26299970 | GSE71289 | Sample source | Moderate | Human iPSC-derived neural progenitor cells
SRP061682 | 26299970 | GSE71289 | Assay type | Severe | all cases are TALENs/CRISPR-Cas9 mutated for DISC1
SRP073163 | 27117414 | GSE80170 | Post alignment | Severe | <3 replicates per group
SRP074904
SRP090259 | 27992436 | GSE87194 | Sequencing | Severe | SOLiD dataset
SRP117268 | 28972157 | GSE103715 | Assay type | Severe | No case samples
SRP135926 | 29727680 | GSE111977 | Assay type | Severe | No case samples
SRP159245 | 38483902 | GSE119316 | Assay type | Severe | all cases are knockdown or gof
SRP188549 | 34151300 | GSE128367 | Assay type | Severe | all cases are ATP6V1A knockdowns
SRP201367 |  | GSE132689
SRP212694 | 40374944 | GSE133615 | Assay type | Severe | all cases are 16p11.2 deletion and duplication
SRP102186 | NA | NA | Sample source | Mild | no covariate information
SRP242009 | 32929213 | GSE143692 | Assay type | Severe | all cases are knockdown POU3F2 , TRIM8
SRP329466 | 35508131 | GSE180648 | Assay type | Severe | all cases are knockdown setd1a+/-
SRP339136 | 34718328 | GSE184930 | Assay type | Moderate | all cases are control vs treatment (control BP vs treatment BP)
SRP344891 | NA | GSE184930 |  |  | No disease vs control info
SRP350706
SRP351616 | 34936134 | GSE191249 | Cohort grouping | Moderate | Mouse cortex transplanted human iPSC-astrocyte progenitors from unaffected twin
SRP351616 | 34936134 | GSE191249 | Sample source | Severe | Skin fibroblast
SRP378256 | NA | GSE205422 | Assay type | Moderate | all cases are control vs treatment (control BP vs treatment BP)
SRP387087 |  | GSE208574 | Post alignment | Moderate | gene-expression changes that result from 16p13.11 CNVs i
SRP396885 | 37117634 | GSE213232 |  |  | sample info available in GSE page
SRP401847 | 36581494 | GSE215183 | Sequencing | Moderate | Copy number variations (CNV) confer high genetic risk for SCZ, with duplication of the 16p11.2 locus increasing risk 14.5 fold.
SRP424801
SRP486687
SRP497832
SRP509182

## Study info
Study_id | publication_link | publication_comparision | publication_covariates | ARTEMIS_Run_ID | ARTEMIS_Main_comparision | Covarites_used
SRP225011 | https://pubmed.ncbi.nlm.nih.gov/32304628/ | Depression vs Control | Sex | 20260508_114303_SRP225011-Depression-2 | Depression vs Control | Sex
SRP323876 | https://pubmed.ncbi.nlm.nih.gov/34848679/ | Chronic vs acute cortisol | None, as the cohort is age and sex matched | 20260508_094621_SRP323876-MDD | MDD Non-responsive_Control vs Healthy_Control, MDD Non-responsive_Chronic Cortisol vs Healthy_Chronic Cortisol, MDD Non-responsive_Chronic Ethanol vs Healthy_Chronic Ethanol, MDD Responsive_Control vs Healthy_Control, MDD Responsive_Chronic Cortisol vs Healthy_Chronic Ethanol, MDD Responsive_Chronic Ethanol vs Healthy_Chronic Ethanol | None, as the cohort is age and sex matched
SRP354339 | https://pubmed.ncbi.nlm.nih.gov/35280164/ | CRH+ interneurons in MDD subjects versus controls | sex, age, postmortem interval and brain pH | 20260507_104732_SRP354339-MDD | sgACC_MDD vs sgACC_control | sex, age, postmortem interval and brain pH
SRP401314 | https://pubmed.ncbi.nlm.nih.gov/37205394/ | MDD vs Control | sex | 20260508_070054_SRP401314-MDD | MDD vs Control | sex
SRP159190 | hsldslkd | sdividsiv | jksdvnindv | jsdbvsndv | sndvnsdv | neoifniqenf
SRP156776 | hsldslkd | sdividsiv | jksdvnindv | jsdbvsndv | sndvnsdv | neoifniqenf

## Daily Log
Date | Done by | Number of datasets completed fully
2026-05-31 | Nischal | 1
2026-06-01 | Nischal | 6
2026-06-02 | Nischal | 4
2026-06-03 | Nischal | 0 | Datasets were not uploaded to Artemis, thus made metadata files for the datasets and worked on the errors which are coming up on BE
2026-06-04 | Nischal | 5

## Remaining
ENA/SRA ID | Diseases | Who? | Done? | Status | Current | PPT made?
ERP001304 | ['Schizophrenia'] | Nischal | No
ERP134591 | ['Schizophrenia'] | Nischal | No
SRP022028 | ['Schizophrenia'] | Nischal | Yes | Artemis completed |  | Yes | Asked for upload on Thursday 21st May but these still havent been uploaded yet
SRP033725 | ['Bipolar disorder'] | Nischal | Yes | Artemis completed |  | Yes | uploaded on 29th!!!
SRP035524 | ['Bipolar disorder'] | Nischal | Processing | BE running |  |  | 2485
SRP043684 | ['Bipolar disorder'] | Nischal | Yes | Artemis completed | Asked for upload | Yes
SRP050376 | ['Schizophrenia'] | Nischal | Yes | Artemis completed | Asked for upload | Yes
SRP050377 | ['Schizophrenia'] | Nischal | Yes | Artemis completed | Asked for upload | Yes
SRP061192 | ['Schizophrenia'] | Nischal | Processing |  | wave | Yes
SRP061682 | ['Schizophrenia'] | Nischal | Processing |  | wave | Yes
SRP073163 | ['Schizophrenia'] | Nischal | Processing |  | wave | Yes
SRP073382 | ['Bipolar disorder'] | Nischal | Processing | Artemis completed | wave | Yes
SRP074904 | ['Bipolar disorder'] | Nischal | Processing | BE error | wave | Yes
SRP089857 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP090259 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP102186 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP117268 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP124299 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP126056 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP135926 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP156776 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes | only 24 samples in samplesheet but there are 56 stated, need to check!! | Checked this and found that the sra database only has 24 srr ids for this srp id
SRP159190 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP159245 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP165962 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP182776 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP183146 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP188467 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP188549 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP201367 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP212636 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP212694 | ['Schizophrenia'] | Nischal | No |  |  | Yes
SRP215268 | ['Bipolar disorder'] | Nischal | Processing |  |  | Yes
SRP223448 | ['Schizophrenia'] | Nischal | Processing |  |  | Yes
SRP241159 | ['Schizophrenia''MDD''BP'] | Suraj | Processing | Uploaded to Artemis |  | Yes
SRP242009 | ['Schizophrenia'] | Suraj | Processing | Uploaded to Artemis |  | Yes
SRP273437 | ['Schizophrenia'] | Suraj | Processing | Uploaded to Artemis |  | Yes
SRP250204 | ['Schizophrenia'] | Suraj | Processing | Uploaded to Artemis |  | Yes
SRP267250 | ['Schizophrenia'] | Suraj | Processing | BE running |  | Yes
SRP246389 | ['Schizophrenia'] | Suraj | No |  | , | Yes
SRP280128 | ['Bipolar disorder'] | Suraj | Processing | BE running |  | Yes
SRP287292 | ['Bipolar disorder'] | Suraj | Processing | BE running |  | Yes
SRP291012 | ['Bipolar disorder'] | Suraj | Processing | BE running |  | No
SRP300746 | ['Schizophrenia'] | Suraj | Processing | BE running |  | Yes
SRP303646 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP329466 | ['Schizophrenia', 'Schizophrenia'] | Suraj | No |  |  | Yes
SRP334277 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP339136 | ['Bipolar disorder'] | Suraj | No |  |  | Yes
SRP344891 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP345441 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP350706 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP351616 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP351617 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP375367 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP378256 | ['Bipolar disorder'] | Suraj | No |  |  | Yes
SRP387087 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP396885 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP401847 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP421233 | ['Schizophrenia', 'Schizophrenia'] | Suraj | No |  |  | Yes
SRP424801 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP443249 | ['Bipolar disorder'] | Suraj | No |  |  | Yes
SRP486687 | ['Schizophrenia', 'Schizophrenia'] | Suraj | No |  |  | Yes
SRP497832 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP509182 | ['Schizophrenia'] | Suraj | No |  |  | Yes
SRP519368 | ['Bipolar disorder'] | Suraj | No
SRP546799 | ['Schizophrenia'] | Suraj | No

## Dashboard used Summary tracker
Dataset Name | Start Date | Status | End Date (BE) | QC Overview | Counts QC overview | Done by | Summary slides | Comments
SRP225011 | 2026-04-27 | Artemis completed | 2026-04-30 | Samples look good | Nothing to note | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_420#slide=id.g3e98e108bb7_2_420 | The study had to be subsampled because some chirp-seq data was present
SRP017329 | NA |  | NA | NA | NA | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_460#slide=id.g3e98e108bb7_2_460 | SOLiD data
SRP323876 | 2026-05-04 | Artemis completed | 2026-05-04 | Nothing to note | Nothing to note | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_475#slide=id.g3e98e108bb7_2_475
SRP354339 | 2026-05-04 | Artemis completed | 2026-05-04 | Nothing to note | Nothing to note | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_525#slide=id.g3e98e108bb7_2_525
SRP548420 | 2026-05-05 | Artemis completed | 2026-05-12 | Nothing to note, some samples are single ended | More variance in a single cell type | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_928#slide=id.g3e98e108bb7_2_928
SRP071203 | 2026-05-11 | Artemis completed | 2026-05-11 | Nothing to note | Nothing to note | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e98e108bb7_2_624#slide=id.g3e98e108bb7_2_624 | No covariate information, unable to find DGEs in the paper, need to decide if this needs to be removed!
SRP329466 | 2026-05-11 | Artemis completed | 2026-05-12 | Removed 5 samples because of significant less number of reads mapped | Nothing to note | Nischal | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e9fa34dab1_0_148#slide=id.g3e9fa34dab1_0_148 | No disease vs control as there is knockdown vs control
SRP022028 | 2026-05-19 | Artemis Error | 2026-05-29 | Nothing to note | Artemis finished partially, not sure about the error | Nischal
SRP033725 | 2026-05-19 | Artemis completed | 2026-05-29 | Nothing to note | Separate clusters for different instruments will have to rerun this after separating different types of instrument
SRP022028 | 2026-05-19 | Artemis running | 2026-05-26 | The samples look fine, but all of them have low mapped reads |  |  | [Link to PPT Slide 11]
SRP033725 | 2026-05-19 | Artemis running | 2026-05-26 | Samples are from different instruments, ran after Timo suggested to run them combined |  |  | [Link to PPT Slide 25]
SRP043684 | 2026-05-25 | Asked for Artemis upload | 2026-05-29
SRP050376 | 2026-05-20 | Asked for Artemis upload | 2026-05-29
SRP050377 | 2026-05-20 | Asked for Artemis upload | 2026-05-29
SRP061192 | 2025-05-29 | BE error
SRP061682 | 2025-05-29 | BE error
SRP073163 | 2025-05-29 | BE error
SRP073382 | 2025-05-29 | BE error
SRP074904 | 2025-05-29 | BE error
SRP035524 | 2025-05-29 | BE error
SRP159190 | 2025-05-30 | Asked for Artemis upload | 2026-05-29 | 2026-05-29 | Separate clusters for different instruments will have to rerun this after separating different types of instrument |  | https://docs.google.com/presentation/d/1aWoLy5rmf72Z2Wfsd4ECesl3gR4pMLJbMTqdmP6uoE4/edit?slide=id.g3e9fa34dab1_0_148#slide=id.g3e9fa34dab1_0_148